## Sheet1
no | task_id | title | createdDate | startDatePlan | endDatePlan | deadline | dateStart | closedDate | responsible | createdBy | status
1 | 6546 | 0.1 TEST TASK | 10-May-2023 12:28 PM |  |  | 11-May-2023 04:30 PM |  | 15-May-2023 02:35 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
2 | 3636 | 2/2023 - GD/NIL - Digital Infrastructure | 23-Jan-2023 07:04 AM | 23-Jan-2023 07:04 AM |  |  | 23-Jan-2023 07:54 AM |  | Bhuvanesh Ayyasamy | Bernard George | Pending
3 | 5498 | ACT Fibernet Installation | 21-Mar-2023 02:21 PM |  |  | 19-Apr-2023 04:30 PM | 05-Apr-2023 12:32 PM | 18-Apr-2023 07:03 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
4 | 5692 | Accounts Team Mail Migration | 29-Mar-2023 09:45 PM |  |  | 03-Apr-2023 08:30 PM | 03-Apr-2023 05:30 PM | 24-Apr-2023 08:52 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
5 | 8038 | Analyse and report the nocix abuse incident | 19-Jun-2023 06:50 AM | 19-Jun-2023 04:30 AM | 19-Jun-2023 08:30 AM | 19-Jun-2023 04:30 PM |  | 19-Jun-2023 11:56 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
6 | 5506 | Apartment 5th Floor Extension process. | 21-Mar-2023 02:40 PM |  |  |  | 04-Apr-2023 03:30 PM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
7 | 6182 | Architect seating arrangement near Mrs.Lumine. | 22-Apr-2023 12:34 PM |  |  | 24-Apr-2023 04:30 PM |  | 01-May-2023 10:38 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
8 | 6186 | Arrange the screen for the dining hall(404). | 22-Apr-2023 12:36 PM |  |  | 27-Apr-2023 04:30 PM |  | 25-Apr-2023 05:28 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
9 | 5854 | Auditor Office Support to ShriHari | 04-Apr-2023 01:40 PM |  |  |  | 06-Apr-2023 07:20 AM | 15-May-2023 02:49 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
10 | 6754 | BSNL AIR Fiber Enquiry and Installation | 15-May-2023 02:25 PM |  |  | 30-May-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
11 | 3670 | Bitrix installation and configuration for external access. | 23-Jan-2023 08:12 AM | 14-Dec-2022 06:30 AM | 29-Dec-2022 04:30 PM |  |  | 21-Mar-2023 03:51 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
12 | 6960 | Business card and Sign Board print | 17-May-2023 06:53 AM |  |  | 18-May-2023 03:30 PM |  | 22-May-2023 09:03 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
13 | 5502 | CCTV Installation and Configurations | 21-Mar-2023 02:24 PM |  |  | 25-May-2023 04:30 PM | 11-Apr-2023 01:37 AM | 25-May-2023 08:11 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
14 | 8342 | CCTV configurations in PNG with Mr.Venkat. | 26-Jun-2023 08:01 AM | [5 empty] | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
15 | 6926 | CEO system Internet connectivity issue | 16-May-2023 09:51 PM |  |  | 18-May-2023 04:30 PM |  | 16-May-2023 09:51 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
16 | 6756 | Check the laptop's condition and refurbish it. | 15-May-2023 02:26 PM |  |  | 26-May-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
17 | 6748 | Cloudflare functionalities discussion | 15-May-2023 01:01 PM |  |  | 31-May-2023 04:30 PM | 15-May-2023 01:03 PM | 26-Jun-2023 06:51 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
18 | 5852 | Create GREEN Maestros Google Workspace | 04-Apr-2023 10:10 AM |  |  | 14-Apr-2023 04:30 PM |  | 14-Apr-2023 06:34 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
19 | 6794 | DIS - Infra Service Tickets | 16-May-2023 05:33 AM |  |  | 22-May-2023 06:30 PM |  | 22-May-2023 08:14 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
20 | 6070 | DIS - Infra Support | 17-Apr-2023 06:28 AM |  |  | 05-May-2023 04:30 PM |  | 06-May-2023 08:58 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
21 | 6514 | DIS - Infra Support | 08-May-2023 10:00 PM |  |  | 15-May-2023 04:30 PM |  | 15-May-2023 07:18 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
22 | 7168 | DIS - Infra Ticket Support | 23-May-2023 07:10 PM |  |  | 30-May-2023 07:30 PM |  | 31-May-2023 08:06 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
23 | 15868 | DIS - Infra documents preparation for system and ISO audit requirement | 27-Nov-2023 07:06 AM |  |  | 27-Nov-2023 04:30 PM |  | 29-Nov-2023 04:48 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
24 | 16980 | DIS - Infra support tickets support. | 08-Jan-2024 06:25 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
25 | 16978 | DIS -Cloud server backup to external drive. | 08-Jan-2024 06:24 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
26 | 15866 | DIS -Cloud server backup to external drive. | 27-Nov-2023 07:04 AM |  |  | 06-Jan-2024 03:00 PM | 04-Jan-2024 08:20 PM | 08-Jan-2024 06:23 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
27 | 8030 | DIS Support and Infra Service Tickets | 19-Jun-2023 05:23 AM |  |  | 30-Jun-2023 08:30 PM |  | 30-Jun-2023 08:57 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
28 | 7432 | DNS Hosting and SSL Implementation | 29-May-2023 06:56 AM |  |  | 31-May-2023 08:30 PM |  | 06-Jun-2023 08:44 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
29 | 5532 | DNS Records Verification and Documentation for GREEN website. | 22-Mar-2023 10:36 PM | 20-Jun-2023 04:30 AM | 20-Jun-2023 12:30 PM | 22-Jun-2023 08:30 PM |  | 26-Jun-2023 06:53 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
30 | 12134 | Deploy and configure the gprogress.green.com.pg URL with server | 10-Aug-2023 05:54 PM |  |  | 11-Aug-2023 04:30 PM |  | 10-Aug-2023 05:56 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
31 | 7612 | Digital assets inventory update. | 05-Jun-2023 07:06 AM |  |  | 13-Jan-2024 03:00 PM | 04-Jan-2024 06:40 AM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
32 | 5976 | Domain name transfer from network solutions | 12-Apr-2023 07:11 AM |  |  | 14-Apr-2023 04:30 PM | 14-Apr-2023 06:34 PM | 14-Apr-2023 06:34 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
33 | 5686 | Donate systems to the School | 29-Mar-2023 09:25 PM |  |  | 17-May-2023 04:30 PM |  | 22-May-2023 08:59 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
34 | 5504 | Elevator 5th Floor Extension and Process | 21-Mar-2023 02:26 PM | [5 empty] | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
35 | 6020 | Enable the mobile phone device management | 13-Apr-2023 07:33 AM |  |  | 14-Apr-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
36 | 16762 | Explain about the bitrix funactionalites to Mr.Sivaraj | 03-Jan-2024 07:57 AM |  |  | 03-Jan-2024 03:00 PM | 03-Jan-2024 07:57 AM | 03-Jan-2024 08:43 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
37 | 6722 | Explain the Bitrix24 Tasks, Sub tasks and Task summary | 15-May-2023 10:56 AM |  |  | 18-May-2023 04:30 PM | 15-May-2023 10:57 AM | 22-May-2023 09:02 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
38 | 6176 | Fast tag activation and load cash for EV. | 22-Apr-2023 12:31 PM |  |  | 22-Apr-2023 04:30 PM |  | 24-Apr-2023 08:52 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
39 | 5708 | Fix the damaged tiles and floors in parking. | 30-Mar-2023 05:34 AM |  |  | 03-May-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
40 | 8322 | GREEN Digitall URL redirect to nexttechnosolutions.com. | 26-Jun-2023 07:06 AM |  |  | 26-Jun-2023 10:30 AM |  | 29-Jun-2023 12:42 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
41 | 6068 | GREEN Maestros finac emails merging | 17-Apr-2023 06:27 AM |  |  | 13-Jul-2023 08:30 PM | 22-Apr-2023 06:12 AM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
42 | 6364 | GREEN website hosting in cloudflare | 03-May-2023 06:57 PM |  |  | 04-May-2023 04:30 AM | 04-May-2023 02:22 AM | 06-May-2023 08:59 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
43 | 5856 | General Activity Support | 04-Apr-2023 01:45 PM |  |  |  | 07-Apr-2023 01:44 PM | 19-Jun-2023 05:09 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
44 | 9010 | General activity support. | 10-Jul-2023 07:23 AM |  |  | 16-Dec-2023 03:00 PM |  | 08-Jan-2024 06:23 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
45 | 8336 | General activity support. | 26-Jun-2023 07:20 AM |  |  | 30-Jun-2023 04:30 PM |  | 30-Jun-2023 08:58 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
46 | 8616 | General activity support. | 03-Jul-2023 07:43 AM |  |  | 07-Jul-2023 04:30 PM |  | 10-Jul-2023 07:06 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
47 | 16976 | General activity support. | 08-Jan-2024 06:24 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
48 | 5710 | Getting the NOC and Resignation from Balasubramani Auditor | 30-Mar-2023 07:16 AM | 27-Mar-2023 06:30 AM |  | 30-Mar-2023 04:30 PM |  | 30-Mar-2023 08:27 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
49 | 6966 | Give an overview to the inventory in the Bitrix24. | 17-May-2023 04:38 PM |  |  | 17-May-2023 05:30 PM |  | 17-May-2023 05:36 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
50 | 15694 | Google Workspace Billing discussion | 20-Nov-2023 07:30 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
51 | 5826 | Guest house cleaning | 03-Apr-2023 12:10 PM |  |  | 03-Apr-2023 04:30 PM | 03-Apr-2023 12:14 PM | 03-Apr-2023 02:57 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
52 | 5688 | HDMI Cable for CEO's System | 29-Mar-2023 09:34 PM |  |  | 31-Mar-2023 04:30 PM |  | 03-Apr-2023 05:12 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
53 | 12408 | Host and configure the green-beta website. | 14-Aug-2023 08:56 PM |  |  | 14-Aug-2023 04:30 PM |  | 20-Aug-2023 03:15 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
54 | 5832 | Hotel booking and followup with Mr.Sagayam from elasticcart. | 03-Apr-2023 05:37 PM |  |  | 04-Apr-2023 04:30 PM | 05-Apr-2023 06:32 AM | 05-Apr-2023 06:41 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
55 | 8334 | Improve the security standards and procedures Analysis - Maleware, antivirus software, and firewall. | 26-Jun-2023 07:14 AM |  |  | 12-Jul-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
56 | 5706 | Improve the websites performance using online testing tools | 30-Mar-2023 05:32 AM |  |  | 04-Jul-2023 10:30 AM |  | 10-Jul-2023 07:05 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
57 | 3660 | Infra Service Tickets | 23-Jan-2023 07:55 AM | 01-Dec-2022 06:30 AM | 30-Dec-2022 04:30 PM |  | 10-Apr-2023 02:26 PM | 15-May-2023 07:19 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
58 | 5508 | Infra Support | 21-Mar-2023 03:50 PM |  |  | 14-Apr-2023 04:30 PM |  | 14-Apr-2023 06:35 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
59 | 9008 | Infra support tickets support | 10-Jul-2023 07:22 AM |  |  | 06-Jan-2024 03:00 PM | 05-Jan-2024 04:22 AM | 08-Jan-2024 06:22 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
60 | 7600 | Infra support tickets support | 05-Jun-2023 06:54 AM |  |  | 16-Jun-2023 06:30 PM |  | 19-Jun-2023 04:52 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
61 | 8614 | Infra support tickets support | 03-Jul-2023 07:42 AM |  |  | 07-Jul-2023 08:30 PM | 03-Jul-2023 07:51 AM | 10-Jul-2023 07:06 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
62 | 6222 | Internet down alert notification. | 25-Apr-2023 07:29 PM |  |  | 28-Apr-2023 04:30 PM |  | 06-May-2023 08:59 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
63 | 15690 | Jio Broadband Bill cycle upgrade monthly into Yearly. | 20-Nov-2023 07:28 AM |  |  | 20-Nov-2023 04:30 PM |  | 20-Nov-2023 08:31 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
64 | 15692 | Jio broadband Billing payment followup with accounts team. | 20-Nov-2023 07:29 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
65 | 7442 | Meeting room setup analysis and improve the group calling | 29-May-2023 06:57 AM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
66 | 8142 | Meeting room test call for quality improvement | 20-Jun-2023 01:53 PM | 20-Jun-2023 02:00 PM | 20-Jun-2023 02:10 PM | 20-Jun-2023 04:30 PM |  | 26-Jun-2023 07:17 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
67 | 3678 | Merging the Google workspace mails | 23-Jan-2023 08:59 AM | 26-Dec-2022 06:30 AM | 31-Jan-2023 04:30 PM |  | 24-Jan-2023 03:47 AM | 21-Mar-2023 04:04 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
68 | 16298 | Nocix VM unable to connect problem resolving | 11-Dec-2023 07:55 PM |  |  | 12-Dec-2023 03:00 PM |  | 08-Jan-2024 06:23 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
69 | 5834 | PNG Requirement Online Order | 03-Apr-2023 06:53 PM |  |  |  | 06-Apr-2023 06:30 PM | 08-Apr-2023 05:50 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
70 | 6178 | Prepare PO for single AC unit(404) to Fujiaire | 22-Apr-2023 12:33 PM | [5 empty] | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
71 | 12410 | Prepare a proxy server for PNG | 14-Aug-2023 08:58 PM |  |  | 19-Aug-2023 04:30 PM |  | 20-Aug-2023 03:15 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
72 | 5828 | Prepare a system for interns | 03-Apr-2023 02:59 PM |  |  | 04-Apr-2023 04:30 PM |  | 05-Apr-2023 12:31 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
73 | 5850 | Preparing system for interns | 04-Apr-2023 07:36 AM |  |  | 04-Apr-2023 04:30 PM | 04-Apr-2023 07:36 AM | 04-Apr-2023 09:53 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
74 | 12068 | SCM - Create Documentation for the Coffee wet plant machines functionalities | 09-Aug-2023 06:39 PM |  |  | 14-Aug-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
75 | 5624 | SSL Analysis and Configuration | 27-Mar-2023 08:37 AM |  |  | 28-Mar-2023 04:30 PM |  | 30-Jun-2023 08:59 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
76 | 16466 | System allocation and Bitrix Email user account creation for new joiner. | 18-Dec-2023 07:16 AM |  |  | 02-Jan-2024 03:00 PM |  | 03-Jan-2024 08:31 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
77 | 6544 | TEST | 10-May-2023 12:23 PM |  |  | 10-May-2023 04:30 PM | 10-May-2023 12:23 PM | 15-May-2023 02:36 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
78 | 6366 | The Nocix Server Backup | 03-May-2023 06:59 PM |  |  | 04-May-2023 05:30 AM | 04-May-2023 02:22 AM | 13-May-2023 08:54 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
79 | 6272 | The Nocix Server troubleshooting | 27-Apr-2023 11:20 PM |  |  | 04-May-2023 04:30 PM | 02-May-2023 04:34 AM | 13-May-2023 08:53 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
80 | 6188 | The kitchen is to be relocated to 403. | 22-Apr-2023 12:36 PM |  |  | 24-Apr-2023 04:30 PM |  | 24-Apr-2023 08:50 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
81 | 6184 | The server relocation to the kitchen(404). | 22-Apr-2023 12:35 PM |  |  | 26-Apr-2023 04:30 PM |  | 25-Apr-2023 05:31 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
82 | 5496 | Ticket SPA Creation and Functional Implementation. | 21-Mar-2023 02:20 PM |  |  | 04-Apr-2023 04:30 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
83 | 6958 | To get back EV RC books from RTO. | 17-May-2023 06:51 AM |  |  | 16-Dec-2023 03:00 PM | 22-May-2023 09:09 AM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
84 | 5690 | Transit and Business Visa Process | 29-Mar-2023 09:37 PM |  |  | 31-Mar-2023 04:30 PM |  | 05-Apr-2023 04:36 PM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
85 | 5862 | Try to configure the letsencrypt SSL for a specific URL and Wildcard URL | 04-Apr-2023 03:11 PM |  |  |  | 04-Apr-2023 03:31 PM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
86 | 6180 | UI and UX team relocate to 404 dining hall. | 22-Apr-2023 12:34 PM |  |  | 25-Apr-2023 04:30 PM |  | 26-Apr-2023 05:58 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
87 | 5500 | Update Inventory List for the Amazon Orders | 21-Mar-2023 02:23 PM |  |  | 16-Aug-2023 06:30 PM | 22-Apr-2023 06:12 AM | 27-Nov-2023 07:02 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
88 | 12136 | Update the cloudflare configurations into improve the website loading time. | 10-Aug-2023 06:00 PM |  |  | 16-Aug-2023 04:30 PM |  | 20-Nov-2023 07:26 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
89 | 8104 | Visit the RTO office and revert the EV's RC cancellation. and get the EV's RC. | 19-Jun-2023 12:18 PM |  |  | 13-Jan-2024 03:00 PM |  |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Pending
90 | 7606 | Yandex mail backup and merge with google workspace POC. | 05-Jun-2023 06:57 AM |  |  | 11-Jul-2023 06:30 PM | 19-Jun-2023 11:57 AM |  | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | In Progress
91 | 8332 | greentelemed.com.pg, next.com.pg DNS migration and DNS records verify from the cloudflare. | 26-Jun-2023 07:14 AM |  |  | 04-Jul-2023 06:30 PM |  | 10-Jul-2023 07:05 AM | Bhuvanesh Ayyasamy | Bhuvanesh Ayyasamy | Completed
92 | 16280 | preparing packing slip for medical items | 11-Dec-2023 06:06 AM |  |  | 13-Dec-2023 03:00 PM |  |  | Bhuvanesh Ayyasamy | Shivakumar Janakiraman | Pending
93 | 6724 | test | 15-May-2023 11:50 AM |  |  | 15-May-2023 04:30 PM |  | 15-May-2023 02:34 PM | Bhuvanesh Ayyasamy | Shivakumar Janakiraman | Completed